## Test Design(Stage3)
Project Name: |  | Php Travels |  |  |  | https://phptravels.net/login
Module Name: |  | Login(Admin Back End)
Reference Document:
Created by: |  | Janza Rasheed A
Date of creation: |  | 2023-01-20
Date of review:
TEST CASE ID | TEST STEP# | Application/features/functions/screen | Test case/step description | Prerequisites | TEST DATA | EXPECTED RESULT | Business priority [High/Medium/Low] | Iteration | Cross-Validation Method | Actual Result | Defect [Y/N]
TC_ADLOG_001 | TST_LGAD_01 | Login Page | Verify whether the admin is able to open webpage on entering the url | Url of the webpage | https://www.phptravels.net/admin | Phptravels admin login page opens which contains the login form | HIGH |  |  | User navigates to php travels admin page | N
[8 empty] | 1 | NA
TC_ADLOG_002 | TST_LGAD_02 | Login page | Enter valid User Name and valid Password | 1. Valid User Name | admin@phptravels.com | Successful login | HIGH |  |  | User was able to login successfully and redirects to the dashboard. | N
|  |  |  | 2. Valid Password | demoadmin |  |  | 1 | NA
TC_ADLOG_003 | TST_LGAD_03 | Login page | Enter invalid User Name and valid Password | 1. Invalid User Name | admin123 | A message "The Email field must contain a valid email address." is shown | HIGH |  |  | A message "The Email field must contain a valid email address." is shown | N
|  |  |  | 2. Valid Password | demoadmin |  |  | 1 | NA
TC_ADLOG_004 | TST_LGAD_04 | Login page | Enter valid User Name and invalid Password | 1. Valid User Name | admin@phptravels.com | A message "Invalid Login Credentialsn" is shown | HIGH |  |  | A message "Invalid Login Credentials" is shown | N
|  |  |  | 2. Invalid Password | DEMO123 |  |  | 1 | NA
TC_ADLOG_005 | TST_LGAD_05 |  | Enter invalid User Name and invalid Password | 1. Invalid User Name | admin123@gmail.com | A message "Invalid Login Credentials" is shown | HIGH |  | NA | A message "Invalid Login Credentials" is shown | N
|  | Login Page |  | 2. Invalid Password | DEMO123 |  |  | 1
Project Name: |  | Php Travels |  |  |  | https://phptravels.net/login
Module Name: |  | ADMIN DASHBOARD
Reference Document:
Created by: |  | Janza Rasheed A
Date of creation: |  | 2023-01-20
Date of review:
TEST CASE ID | TEST STEP# | Application/features/functions/screen | Test case/step description | Prerequisites | TEST DATA | EXPECTED RESULT | Business priority [High/Medium/Low] | Iteration | Cross-Validation Method | Actual Result | Defect [Y/N]
TC_DADMIN_001 | TST_DAD_01 | Admin Dashboard | Verify whether the page displays the revenue breakdown statictics in a bar graph | User logged in as an admin | NA | Dashboard should display the bar graph for the revenue breakdown for the current year | HIGH | 1 | NA | Dashboard display the bar graph for the revenue breakdown for the year 2023 | N
TC_DADMIN_002 | TST_DAD_02 | Admin Dashboard | Verify whether the page displays a pie chart for the search history with the values for hotels, tours, cars, visas and flight with the number displayed at the bottom | User logged in as an admin | NA | Dashboard should display a pie chart for the search history with the values for hotels, tours, cars, visas and flight with the number displayed at the bottom | HIGH | 1 | NA | Dashboard displays a pie chart for the search history with the values for hotels, tours, cars, visas and flight with the number displayed at the bottom | N
TC_DADMIN_003 | TST_DAD_03 | Admin Dashboard | Verify whether the dashboad top menu with the items like website booking and docs | User logged in as an admin | NA | The dashboard should displays top menu with the items like website, booking and docs and are clickable | HIGH | 1 | NA | The dashboard displays top menu with the items like website, booking and docs and are clickable | N
TC_DADMIN_004 | TST_DAD_04 | Admin Dashboard | Verify whether the user navigates to main website on clicking on Website on top menu | User logged in as an admin | NA | The user navigetes to https://phptravels.net/ | HIGH | 1 | NA | The user navigetes to https://phptravels.net/ | N
TC_DADMIN_005 | TST_DAD_05 | Admin Dashboard | Check whether user is able to view all bookings on clicking on the Bookings on Top menu | User logged in as an admin | NA | The user navigetes to https://phptravels.net/api/admin/bookings and is able to view all the booking details | HIGH | 1 | NA | The user navigetes to https://phptravels.net/api/admin/bookings and is able to view all the booking details | N
TC_DADMIN_006 | TST_DAD_06 | Admin Dashboard | Check whether user redirects to documentation page of phptravels on clicking on docs | User logged in as an admin | NA | The user should redirect to the https://docs.phptravels.com/ | HIGH | 1 | NA | The user should redirect to the https://docs.phptravels.com/ | N
TC_DADMIN_007 | TST_DAD_07 | Admin Dashboard | Check the left panel menu of the dashboard | User logged in as an admin | NA | The dashboard should display the left panel witt the main items like dashborad,settings, modules, accounts, CMS. It also has two more main divisions like modules and extras. Modules has divisions like cars, flights, hotels visa and tours. Extras hold options likeoffers, blog, location,coupens, newsletters, payouts and bookings | HIGH | 1 | NA | The dashboard should display the left panel witt the main items like dashborad,settings, modules, accounts, CMS. It also has two more main divisions like modules and extras. Modules has divisions like cars, flights, hotels visa and tours. Extras hold options likeoffers, blog, location,coupens, newsletters, payouts and bookings | N
TC_DADMIN_008 | TST_DAD_08 | Admin Dashboard | Check whether user icon displays options to logout | User logged in as an admin | NA | The dashboard should display options like profile,settings, help, logout | HIGH |  | NA | The dashboard should display options like profile,settings, help, logout | N
TC_DADMIN_009 | TST_DAD_09 | Admin Dashboard- Settings | Check whether user gets different settings options on clicking settings on the left panel menu | User logged in as an admin | NA | On clicking settings it should display options like general settings, Updates, Currencies, Payment gate ways, Social connections, Homepage sliders, Email templates, SMS api settings, Backup and Ban IP. | HIGH |  | NA | On clicking settings it should display options like general settings, Updates, Currencies, Payment gate ways, Social connections, Homepage sliders, Email templates, SMS api settings, Backup and Ban IP. | N
TC_DADMIN_010 | TST_DAD_10 | Admin Dashboard- Modules | Check whether the user navigates to modules page on clicking modules on Left panel menu | User logged in as an admin | NA | Upon clicking the "Modules", user should get redirect to the Module page which displays modules like Hotels, Cars, Flights and Tours with the status | HIGH | 1 | NA | Upon clicking the "Modules", user redirected to the Module page which displays modules like Hotels, Cars, Flights and Tours with the status | N
TC_DADMIN_011 | TST_DAD_11 | Admin Dashboard- Accounts | Check whether user gets different accounts options on clicking settings on the left panel menu | User logged in as an admin | NA | Upon clicking the "Accounts" the user gets different options like Admin, suppliers, Agent, Customers and guest customers | HIGH | 1 | NA | Upon clicking the "Accounts" the user gets different options like Admin, suppliers, Agent, Customers and guest customers | N
TC_DADMIN_012 | TST_DAD_12 | Admin Dashboard- CMS | Check whether user gets different CMS options on clicking settings on the left panel menu | User logged in as an admin | NA | Upon clicking the "CMS" the user gets different options like Pages, Menu | HIGH | 1 | NA | Upon clicking the "CMS" the user gets different options like Pages, Menu | N
TC_DADMIN_013 | TST_DAD_13 | Admin Dashboard- Modules-Cars | Check whether user gets different options on clicking Cars under Modules on the left panel menu | User logged in as an admin | NA | Upon clicking the "Cars" the user gets different options like Transfers, Location, Bookings, Searches. | HIGH | 1 | NA | Upon clicking the "Cars" the user gets different options like Transfers, Location, Bookings, Searches. | N
TC_DADMIN_014 | TST_DAD_14 | Admin Dashboard- Modules-Flights | Check whether user gets different options on clicking Flights under Modules on the left panel menu | User logged in as an admin | NA | Upon clicking the "Flights" the user gets different options like Flights, Amdeus, Duffel, Kiwi,Aertickets, Tranfers, Searches | HIGH | 1 | NA | Upon clicking the "Flights" the user gets different options like Flights, Amdeus, Duffel, Kiwi,Aertickets, Tranfers, Searches | N
TC_DADMIN_015 | TST_DAD_15 | Admin Dashboard- Modules-Hotels | Check whether user gets different options on clicking Hotels under Modules on the left panel menu | User logged in as an admin | NA | Upon clicking the "Flights" the user gets different options like Hotels, Rezlives, Agoda,Location, bookings, searches. | HIGH | 1 | NA | Upon clicking the "Flights" the user gets different options like Hotels, Rezlives, Agoda,Location, bookings, searches. | N
TC_DADMIN_016 | TST_DAD_16 | Admin Dashboard- Modules-Visa | Check whether user gets different options on clicking Visa under Modules on the left panel menu | User logged in as an admin | NA | Upon clicking the "Visa" the user gets different options like Visa, Bookings, searches. | HIGH | 1 | NA | Upon clicking the "Visa" the user gets different options like Visa, Bookings, searches. | N
TC_DADMIN_017 | TST_DAD_17 | Admin Dashboard- Modules-Tours | Check whether user gets different options on clicking Tours under Modules on the left panel menu | User logged in as an admin | NA | Upon clicking the "Tours" the user gets different options like Tiquets, Tours, Vaitor, loaction, bookings, searches | HIGH | 1 | NA | Upon clicking the "Tours" the user gets different options like Tiquets, Tours, Vaitor, loaction, bookings, searches | N
TC_DADMIN_018 | TST_DAD_18 | Admin Dashboard- Extras-offers | Check whether user gets different options on clicking offers under Extras on the left panel menu | User logged in as an admin | NA | Upon clicking the "offers" the user gets different options like Manage offer, Offer settings | HIGH | 1 | NA | Upon clicking the "offers" the user gets different options like Manage offer, Offer settings | N
TC_DADMIN_019 | TST_DAD_19 | Admin Dashboard- Extras-Blog | Check whether user gets different options on clicking on Blog under Extras on the left panel menu | User logged in as an admin | NA | Upon clicking the "Blog" the user gets different options like post,Blog categories, Blog settings | HIGH | 1 | NA | Upon clicking the "Blog" the user gets different options like post,Blog categories, Blog settings | N
TC_DADMIN_020 | TST_DAD_20 | Admin Dashboard- Extras-Location | Check whether user gets redirected to Locations page where the admin can add or delete location information | User logged in as an admin | NA | Upon clicking the "Location" the user gets redirected to location screen which contains buttons to add and delete locations and also displays different locations as a list providing city name, country lattitude, longitude, and status | HIGH | 1 | NA | Upon clicking the "Location" the user gets redirected to location screen which contains buttons to add and delete locations and also displays different locations as a list providing city name, country lattitude, longitude, and status | N
TC_DADMIN_021 | TST_DAD_21 | Admin Dashboard- Extras-Coupon | Check whether user gets redirected to Coupon code management page where the admin can add or delete coupon information | User logged in as an admin | NA | Upon clicking the "Coupon" the user gets redirected to Coupon code mangement s screen which contains buttons to add and delete locations and also displays a list containing coupon code, Rate%, Max uses, Used so far, Start date, Expiration date,Enabled | HIGH | 1 | NA | Upon clicking the "Coupon" the user gets redirected to Coupon code mangement s screen which contains buttons to add and delete locations and also displays a list containing coupon code, Rate%, Max uses, Used so far, Start date, Expiration date,Enabled | N
TC_DADMIN_022 | TST_DAD_22 | Admin Dashboard- Extras-Newsletter | Check whether user gets redirected to Newsletter page where the admin can add or delete coupon information | User logged in as an admin | NA | Upon clicking the "Newsletter" the user gets redirected to Newsletter screen which contains button delete and also displays a list containing Newsletter subscriber, type, Enabled. | HIGH | 1 | NA | Upon clicking the "Newsletter" the user gets redirected to Newsletter screen which contains button delete and also displays a list containing Newsletter subscriber, type, Enabled. | N
TC_DADMIN_023 | TST_DAD_23 | Admin Dashboard- Extras-Payout | Check whether user gets different options on clicking Payout under Extras on the left panel menu | User logged in as an admin | NA | Upon clicking the "Payoutr" the user getsdifferent options like Tranfers, Hotels, Tours | HIGH | 1 | NA | Upon clicking the "Payoutr" the user getsdifferent options like Tranfers, Hotels, Tours | N
TC_DADMIN_024 | TST_DAD_24 | Admin Dashboard- Extras-Bookings | Check whether user is able to view all bookings on clicking on the Bookings on LEFT menu | User logged in as an admin | NA | The user navigetes to https://phptravels.net/api/admin/bookings and is able to view all the booking details | HIGH | 1 | NA | The user navigetes to https://phptravels.net/api/admin/bookings and is able to view all the booking details | N
Project Name: |  | Php Travels |  |  |  | https://phptravels.net/login
Module Name: |  | Bookings-Admin Back End
Reference Document:
Created by: |  | Janza Rasheed A
Date of creation: |  | 2023-01-20
Date of review:
TEST CASE ID | TEST STEP# | Application/features/functions/screen | Test case/step description | Prerequisites | TEST DATA | EXPECTED RESULT | Business priority [High/Medium/Low] | Iteration# | Cross-Validation Method | Actual Result | Defect [Y/N]
TC_BADMIN_001 | TST_BAD_01 | Bookings | Check whether user is able to view all bookings on clicking on the Bookings on Top menu | User logged in as an admin | NA | My booking page should display "Hi, Username Welcome Back | HIGH | 1 | NA | My booking page should display "Hi, Username Welcome Back | N
TC_BADMIN_002 | TST_BAD_02 | Bookings | Verify whether the user can view the number of all types of bookings | User logged in as an admin | NA | Bookings page displays the number of pending, cancelled, paid, confirmed,unpaid and refunded bookings | HIGH | 1 | NA | Bookings page displays the number of pending, cancelled, paid, confirmed,unpaid and refunded bookings | N
TC_BADMIN_003 | TST_BAD_03 | Bookings | Verify whether the admin gets redirected to invoice page on clicking on any invoice button provided in the bookings data list | User logged in as an admin | NA | The page redirects to invoice page which displays Payment, Booking Invoice , Booking Details and Guest Information | HIGH | 1 | NA | The page redirects to invoice page which displays Payment, Booking Invoice , Booking Details and Guest Information | N
TC_BADMIN_004 | TST_BAD_04 | Bookings cancellation | Verify whether the admin can delete the record having booking status as cancelled | User logged in as an admin | NA | Upon clicking the Canceled Bookings from the Admin dashboard, it will show the list of canceled booking records (if any) | HIGH | 1 | NA | Upon clicking the Canceled Bookings from the Admin dashboard, it will show the list of canceled booking records (if any) | N
TC_BADMIN_005 | TST_BAD_05 | Bookings cancellation | Verify whether the data got deleted present in the list of records | User logged in as an admin | NA | Record should be removed from the list upon clicking the RED colored delete button | HIGH | 1 | NA | Record should be removed from the list upon clicking the RED colored delete button | N
TC_BADMIN_006 | TST_BAD_06 | Bookings pending to confirmed | Verify whether the admin can change a booking status from pending to confirmed | User logged in as an admin | NA | The admin should be able to change the booking status from pending to confirmed | HIGH | 1 | NA | The admin should be able to change the booking status from pending to confirmed | N
TC_BADMIN_007 | TST_BAD_07 | Bookings pending to confirmed | Verify whether the count got reflected when booking status was changed from pending to confimed | User logged in as an admin | NA | The count number decreased by 1 in pending Bookings and increased by 1 in confirmed booking | HIGH | 1 | NA | The count number decreased by 1 in pending Bookings and increased by 1 in confirmed booking | N
Project Name: |  | Php Travels |  |  |  | https://phptravels.net/login
Module Name: |  | Website(Admin Back End)
Reference Document:
Created by: |  | Janza Rasheed A
Date of creation: |  | 2023-01-07
Date of review: |  | 2023-01-07
TEST CASE ID | TEST STEP# | Application/features/functions/screen | Test case/step description | Prerequisites | TEST DATA | EXPECTED RESULT | Business priority [High/Medium/Low] | Iteration | Cross-Validation Method | Actual Result | Defect [Y/N]
TC_WB_001 | TST_WB_01 | Website link | Verify whether the Website link present at the top navigation bar of the admin page | User logged in as an existing agent | NA | Upon clicking the website link it should redirect to it's destination page | HIGH | 1 | NA | Upon clicking the website link it should redirect to it's destination page | N
Project Name: |  | Php Travels |  |  |  | https://phptravels.net/login
Module Name: |  | Logout(Admin Back End)
Reference Document:
Created by: |  | Janza Rasheed A
Date of creation: |  | 2023-01-20
Date of review:
TEST CASE ID | TEST STEP# | Application/features/functions/screen | Test case/step description | Prerequisites | TEST DATA | EXPECTED RESULT | Business priority [High/Medium/Low] | Iteration | Cross-Validation Method | Actual Result | Defect [Y/N]
TC_ALOGOUT_001 | TST_ALO_01 | Logout | Verify whether the user is able to logout | User logged in as an existing agent | NA | User should be able to logout from their account on clicking the logout button ang redirects to login page | HIGH | 1 | NA | User should be able to logout from their account on clicking the logout button ang redirects to login page | N

## Test Case(stage3)
Project Name: |  |  | Phptravels |  |  |  | https://www.phptravels.net/admin
Module Name: |  |  | Login(Agent Front End)
Created by: |  |  | Janza Rasheed A
Date of creation: |  |  | 2023-01-20
Date of review:
TEST CASE ID | TEST SCENARIO# | Application/features/functions/screen | TEST CASE DESCRIPTION | TEST STEP# | TEST STEPS | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS (PASS/FAIL)
TC_ADLOG_001 | TS014 | Login Page | Verify whether the admin is able to open webpage on entering the url | TST_LGAD_01 | 1. Open a new tab 2. Enter the url 3. Click enter | https://www.phptravels.net/admin | Phptravels admin login page opens which contains the login form | User navigates to php travels admin page | PASS
TC_ADLOG_002 | TS014 |  |  | TST_LGAD_02 | 1. Enter User Name 2. Enter Password 3. Click "Login" button | admin@phptravels.com | Successful login | User was able to login successfully | PASS
|  | Login Page | Enter valid User Name and valid Password |  |  | demoadmin
TC_ADLOG_003 | TS015 | Login Page | Enter invalid User Name and valid Password | TST_LGAD_03 | 1. Enter User Name 2. Enter Password 3. Click "Login" button | admin123 | A message "The Email field must contain a valid email address." is shown | A message "The Email field must contain a valid email address." is shown | PASS
demoadmin
TC_ADLOG_004 | TS015 | Login Page | Enter valid User Name and invalid Password | TST_LGAD_04 | 1. Enter User Name 2. Enter Password 3. Click "Login" button | admin@phptravels.com | A message "Invalid Login Credentialsn" is shown | A message "Invalid Login Credentialsn" is shown | PASS
demo123
TC_ADLOG_005 | TS015 | Login Page | Enter invalid User Name and invalid Password | TST_LGAD_05 | 1. Enter User Name 2. Enter Password 3. Click "Login" button | admin123@gmail.com | A message "Invalid Login Credentialsn" is shown | A message "Invalid Login Credentialsn" is shown | PASS
DEMO123
Project Name: |  |  | Phptravels |  |  |  | https://www.phptravels.net/admin
Module Name: |  |  | Dashboard(Admin Back End)
Created by: |  |  | Janza Rasheed A
Date of creation: |  |  | 2023-01-20
Date of review:
TEST CASE ID | TEST SCENARIO# | Application/features/functions/screen | TEST CASE | TEST STEP# | TEST STEPS | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS (PASS/FAIL)
TC_DADMIN_001 | TS030 | Admin Dashboard | Verify whether the page displays the revenue breakdown statictics in a bar graph | TST_DAD_01 | 1. Login to the dashboard 2. Check the page | NA | Dashboard should display the bar graph for the revenue breakdown for the current year | Dashboard display the bar graph for the revenue breakdown for the year 2023 | PASS
TC_DADMIN_002 | TS030 | Admin Dashboard | Verify whether the page displays a pie chart for the search history with the values for hotels, tours, cars, visas and flight with the number displayed at the bottom | TST_DAD_02 | 1.Login to the dashboard 2.Check the contents in the page | NA | Dashboard should display a pie chart for the search history with the values for hotels, tours, cars, visas and flight with the number displayed at the bottom | Dashboard displays a pie chart for the search history with the values for hotels, tours, cars, visas and flight with the number displayed at the bottom | PASS
TC_DADMIN_003 | TS031 | Admin Dashboard | Verify whether the dashboad top menu with the items like website booking and docs | TST_DAD_03 | 1.Login to the dashboard 2.Check the Top menu in the page | NA | The dashboard should displays top menu with the items like website, booking and docs and are clickable | The dashboard displays top menu with the items like website, booking and docs and are clickable | PASS
TC_DADMIN_004 | TS031 | Admin Dashboard | Verify whether the user navigates to main website on clicking on Website on top menu | TST_DAD_04 | 1.Login to the dashboard 2.Click on Website on top menu | NA | The user navigetes to https://phptravels.net/ | The user navigetes to https://phptravels.net/ | PASS
TC_DADMIN_005 | TS031 | Admin Dashboard | Check whether user is able to view all bookings on clicking on the Bookings on Top menu | TST_DAD_05 | 1.Login to the dashboard 2.Click on Bookings on top menu | NA | The user navigetes to https://phptravels.net/api/admin/bookings and is able to view all the booking details | The user navigetes to https://phptravels.net/api/admin/bookings and is able to view all the booking details | PASS
TC_DADMIN_006 | TS031 | Admin Dashboard | Check whether user redirects to documentation page of phptravels on clicking on docs | TST_DAD_06 | 1.Login to the dashboard 2.Check the Top panel menu in the page 3. Click on docs | NA | The user should redirect to the https://docs.phptravels.com/ | The user should redirect to the https://docs.phptravels.com/ | PASS
TC_DADMIN_007 | TS032 | Admin Dashboard | Check the left panel menu of the dashboard | TST_DAD_07 | 1.Login to the dashboard 2.Check the Left menu in the page | NA | The dashboard should display the left panel witt the main items like dashborad,settings, modules, accounts, CMS. It also has two more main divisions like modules and extras. Modules has divisions like cars, flights, hotels visa and tours. Extras hold options likeoffers, blog, location,coupens, newsletters, payouts and bookings | The dashboard displays the left panel witt the main items like dashborad,settings, modules, accounts, CMS. It also has two more main divisions like modules and extras. Modules has divisions like cars, flights, hotels visa and tours. Extras hold options likeoffers, blog, location,coupens, newsletters, payouts and bookings | PASS
TC_DADMIN_008 | TS031 | Admin Dashboard | Check whether user icon displays options to logout | TST_DAD_08 | 1.Login to the dashboard 2.Check the Top panel menu in the page 3. Click on user icon | NA | The dashboard should display options like profile,settings, help, logout | The dashboard displays options like profile,settings, help, logout | PASS
TC_DADMIN_009 | TS032 | Admin Dashboard- Settings | Check whether user gets different settings options on clicking settings on the left panel menu | TST_DAD_09 | 1.Login to the dashboard 2.Check the Left panel menu in the page 3. Click on Settings | NA | On clicking settings it should display options like general settings, Updates, Currencies, Payment gate ways, Social connections, Homepage sliders, Email templates, SMS api settings, Backup and Ban IP. | On clicking settings it displays options like general settings, Updates, Currencies, Payment gate ways, Social connections, Homepage sliders, Email templates, SMS api settings, Backup and Ban IP. | PASS
TC_DADMIN_010 | TS032 | Admin Dashboard- Modules | Check whether the user navigates to modules page on clicking modules on Left panel menu | TST_DAD_10 | 1.Login to the dashboard 2.Check the left panel menu in the page 3. Click on Modules | NA | Upon clicking the "Modules", user should get redirect to the Module page which displays modules like Hotels, Cars, Flights and Tours with the status | Upon clicking the "Modules", user redirected to the Module page which displays modules like Hotels, Cars, Flights and Tours with the status | PASS
TC_DADMIN_011 | TS032 | Admin Dashboard- Accounts | Check whether user gets different accounts options on clicking settings on the left panel menu | TST_DAD_11 | 1.Login to the dashboard 2.Check the left panel menu in the page 3. Click on Accounts | NA | Upon clicking the "Accounts" the user gets different options like Admin, suppliers, Agent, Customers and guest customers | Upon clicking the "Accounts" the user gets different options like Admin, suppliers, Agent, Customers and guest customers
TC_DADMIN_012 | TS032 | Admin Dashboard- CMS | Check whether user gets different CMS options on clicking settings on the left panel menu | TST_DAD_12 | 1.Login to the dashboard 2.Check the left panel menu in the page 3. Click on CMS | NA | Upon clicking the "CMS" the user gets different options like Pages, Menu | Upon clicking the "CMS" the user gets different options like Pages, Menu | PASS
TC_DADMIN_013 | TS032 | Admin Dashboard- Modules-Cars | Check whether user gets different options on clicking Cars under Modules on the left panel menu | TST_DAD_13 | 1.Login to the dashboard 2.Check the left panel menu in the page 3. Click on Cars | NA | Upon clicking the "Cars" the user gets different options like Transfers, Location, Bookings, Searches. | Upon clicking the "Cars" the user gets different options like Transfers, Location, Bookings, Searches. | PASS
TC_DADMIN_014 | TS032 | Admin Dashboard- Modules-Flights | Check whether user gets different options on clicking Flights under Modules on the left panel menu | TST_DAD_14 | 1.Login to the dashboard 2.Check the left panel menu in the page 3. Click on Flights | NA | Upon clicking the "Flights" the user gets different options like Flights, Amdeus, Duffel, Kiwi,Aertickets, Tranfers, Searches | Upon clicking the "Flights" the user gets different options like Flights, Amdeus, Duffel, Kiwi,Aertickets, Tranfers, Searches | PASS
TC_DADMIN_015 | TS032 | Admin Dashboard- Modules-Hotels | Check whether user gets different options on clicking Hotels under Modules on the left panel menu | TST_DAD_15 | 1.Login to the dashboard 2.Check the left panel menu in the page 3. Click on Hotels | NA | Upon clicking the "Flights" the user gets different options like Hotels, Rezlives, Agoda,Location, bookings, searches. | Upon clicking the "Flights" the user gets different options like Hotels, Rezlives, Agoda,Location, bookings, searches. | PASS
TC_DADMIN_016 | TS032 | Admin Dashboard- Modules-Visa | Check whether user gets different options on clicking Visa under Modules on the left panel menu | TST_DAD_16 | 1.Login to the dashboard 2.Check the left panel menu in the page 3. Click on Visa | NA | Upon clicking the "Visa" the user gets different options like Visa, Bookings, searches. | Upon clicking the "Visa" the user gets different options like Visa, Bookings, searches. | PASS
TC_DADMIN_017 | TS032 | Admin Dashboard- Modules-Tours | Check whether user gets different options on clicking Tours under Modules on the left panel menu | TST_DAD_17 | 1.Login to the dashboard 2.Check the left panel menu in the page 3. Click on Tours | NA | Upon clicking the "Tours" the user gets different options like Tiquets, Tours, Vaitor, loaction, bookings, searches | Upon clicking the "Tours" the user gets different options like Tiquets, Tours, Vaitor, loaction, bookings, searches | PASS
TC_DADMIN_018 | TS032 | Admin Dashboard- Extras-offers | Check whether user gets different options on clicking offers under Extras on the left panel menu | TST_DAD_18 | 1.Login to the dashboard 2.Check the left panel menu in the page 3. Click on Offers | NA | Upon clicking the "offers" the user gets different options like Manage offer, Offer settings | Upon clicking the "offers" the user gets different options like Manage offer, Offer settings | PASS
TC_DADMIN_019 | TS032 | Admin Dashboard- Extras-Blog | Check whether user gets different options on clicking on Blog under Extras on the left panel menu | TST_DAD_19 | 1.Login to the dashboard 2.Check the left panel menu in the page 3. Click on Blog | NA | Upon clicking the "Blog" the user gets different options like post,Blog categories, Blog settings | Upon clicking the "Blog" the user gets different options like post,Blog categories, Blog settings | PASS
TC_DADMIN_020 | TS032 | Admin Dashboard- Extras-Location | Check whether user gets redirected to Locations page where the admin can add or delete location information | TST_DAD_20 | 1.Login to the dashboard 2.Check the left panel menu in the page 3. Click on Location | NA | Upon clicking the "Location" the user gets redirected to location screen which contains buttons to add and delete locations and also displays different locations as a list providing city name, country lattitude, longitude, and status | Upon clicking the "Blog" the user gets redirected to location screen which contains buttons to add and delete locations and also displays different locations as a list providing city name, country lattitude, longitude, and status | PASS
TC_DADMIN_021 | TS032 | Admin Dashboard- Extras-Coupon | Check whether user gets redirected to Coupon code management page where the admin can add or delete coupon information | TST_DAD_21 | 1.Login to the dashboard 2.Check the left panel menu in the page 3. Click on Coupon | NA | Upon clicking the "Coupon" the user gets redirected to Coupon code mangement s screen which contains buttons to add and delete locations and also displays a list containing coupon code, Rate%, Max uses, Used so far, Start date, Expiration date,Enabled | Upon clicking the "Coupon" the user gets redirected to Coupon code mangement s screen which contains buttons to add and delete locations and also displays a list containing coupon code, Rate%, Max uses, Used so far, Start date, Expiration date,Enabled | PASS
TC_DADMIN_022 | TS032 | Admin Dashboard- Extras-Newsletter | Check whether user gets redirected to Newsletter page where the admin can add or delete coupon information | TST_DAD_22 | 1.Login to the dashboard 2.Check the left panel menu in the page 3. Click on Newsletter | NA | Upon clicking the "Newsletter" the user gets redirected to Newsletter screen which contains button delete and also displays a list containing Newsletter subscriber, type, Enabled. | Upon clicking the "Newsletter" the user gets redirected to Newsletter screen which contains button delete and also displays a list containing Newsletter subscriber, type, Enabled. | PASS
TC_DADMIN_023 | TS032 | Admin Dashboard- Extras-Payout | Check whether user gets different options on clicking Payout under Extras on the left panel menu | TST_DAD_23 | 1.Login to the dashboard 2.Check the left panel menu in the page 3. Click on Payout | NA | Upon clicking the "Payoutr" the user getsdifferent options like Tranfers, Hotels, Tours | Upon clicking the "Payoutr" the user getsdifferent options like Tranfers, Hotels, Tours | PASS
TC_DADMIN_024 | TS032 | Admin Dashboard- Extras-Bookings | Check whether user is able to view all bookings on clicking on the Bookings on LEFT menu | TST_DAD_24 | 1.Login to the dashboard 2.Check the left panel menu in the page 3. Click on BOOKINGS | NA | The user navigetes to https://phptravels.net/api/admin/bookings and is able to view all the booking details | The user navigetes to https://phptravels.net/api/admin/bookings and is able to view all the booking details | PASS
Project Name: |  |  | Phptravels |  |  |  | https://www.phptravels.net/admin
Module Name: |  |  | Bookings(Admin Back End)
Created by: |  |  | Janza Rasheed A
Date of creation: |  |  | 2023-01-20
Date of review:
TEST CASE ID | TEST SCENARIO# | Application/features/functions/screen | TEST CASE | TEST STEP# | TEST STEPS | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS (PASS/FAIL)
TC_BADMIN_001 | TS033 | Bookings | Check whether user is able to view all bookings on clicking on the Bookings on Top menu | TST_BAD_01 | 1.Login to the dashboard 2.Click on Bookings on top menu | NA | The user navigetes to https://phptravels.net/api/admin/bookings and is able to view all the booking details | The user navigetes to https://phptravels.net/api/admin/bookings and is able to view all the booking details | PASS
TC_BADMIN_002 | TS033 | Bookings | Verify whether the user can view the number of all types of bookings | TST_BAD_02 | 1.Click on " bookings" 2.Check the Top panel in the page | NA | Bookings page displays the number of pending, cancelled, paid, confirmed,unpaid and refunded bookings | Bookings page displays the number of pending, cancelled, paid, confirmed,unpaid and refunded bookings | PASS
TC_BADMIN_003 | TS033 | Bookings | Verify whether the admin gets redirected to invoice page on clicking on any invoice button provided in the bookings data list | TST_BAD_03 | 1.Click on " bookings" 2.Click on any invoice in the page | NA | The page redirects to invoice page which displays Payment, Booking Invoice , Booking Details and Guest Information | The page redirects to invoice page which displays Payment, Booking Invoice , Booking Details and Guest Information | PASS
TC_BADMIN_004 | TS034 | Bookings cancellation | Verify whether the admin can delete the record having booking status as cancelled | TST_BAD_04 | 1. Login as Admin 2. Click Cancelled Bookings from the top menu | NA | Upon clicking the Canceled Bookings from the Admin dashboard, it will show the list of canceled booking records (if any) | Upon clicking the Canceled Bookings from the Admin dashboard, it will show the list of canceled booking records (if any) | PASS
TC_BADMIN_005 | TS034 | Bookings cancellation | Verify whether the data got deleted present in the list of records | TST_BAD_05 | 1.Login as Admin 2.Click Cancelled Booking 3.Click the RED coloured delete button | NA | Record should be removed from the list upon clicking the RED colored delete button | Record was removed from the list upon clicking the RED colored delete button | PASS
TC_BADMIN_006 | TS035 | Bookings pending to confirmed | Verify whether the admin can change a booking status from pending to confirmed | TST_BAD_06 | 1.Login as Admin 2.Click Booking 3.Click on pending bookings on the top panel 4. Click on the booking status drop down in the list provided. 5. Change the status to confimed | NA | The admin should be able to change the booking status from pending to confirmed | The admin was able to change the booking status from pending to confirmed | PASS
TC_BADMIN_007 | TS035 | Bookings pending to confirmed | Verify whether the count got reflected when booking status was changed from pending to confimed | TST_BAD_07 | 1.Login as Admin 2.Click Booking 3.Click on pending bookings on the top panel 4. Click on the booking status drop down in the list provided. 5. Change the status to confimed | NA | The count number decreased by 1 in pending Bookings and increased by 1 in confirmed booking | The count number decreased by 1 in pending Bookings and increased by 1 in confirmed booking | PASS
Project Name: |  |  | Phptravels |  |  |  | https://phptravels.net/api/admin
Module Name: |  |  | Website(Admin Back End)
Created by: |  |  | Janza Rasheed A
Date of creation: |  |  | 2023-01-20
Date of review:
TEST CASE ID | TEST SCENARIO# | Application/features/functions/screen | TEST CASE | TEST STEP# | TEST STEPS | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS (PASS/FAIL)
TC_WB_001 | TS036 | Website link | Verify whether the Website link present at the top navigation bar of the admin page | TST_WB_01 | 1.Login as Admin 2.Click the Website Link from the left menu | NA | Upon clicking the website link it should redirect to it's destination page | Upon clicking the website link it should redirect to it's destination page | PASS
Project Name: |  |  | Phptravels |  |  |  | https://phptravels.net/api/admin
Module Name: |  |  | Logout(Admin Back End)
Created by: |  |  | Janza Rasheed A
Date of creation: |  |  | 2023-01-20
Date of review:
TEST CASE ID | TEST SCENARIO# | Application/features/functions/screen | TEST CASE DESCRIPTION | TEST STEP# | TEST STEPS | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS (PASS/FAIL)
TC_ALOGOUT_001 | TS037 | Logout | Verify whether the user is able to logout | TST_ALO_01 | 1. Login to the dashboard 2. Click on the user icon 3.Click on Logout | NA | User should be able to logout from their account on clicking the logout button ang redirects to login page | User successfully logged out and redirected to login page | PASS

## Test Scenario(stage3)
TEST SCENARIO
Req ID | Test Scenario ID | Application name/Module name | High Level Condition/Test scenario | Expected Result | Priority
RQ27 | TS027 | Launch the admin webpage | Verify whether the admin is able to open webpage on entering the url | The webpage shoud load successfully at the user end | High
RQ28 | TS028 | Login as an admin | Verify the login functionality using valid username and password | Successful login | High
RQ29 | TS029 | Login as an admin | Verify the login functionality using invalid username and password | User should be able to see appropriate message displayed on the screen and should not be able to login | High
RQ30 | TS030 | Admin Dashboard | Verify the features of Admin dashboard | User should be redirected to the dashboard after logging in and it should display revenue breakdown in bar graph and search history in a pie chart | High
RQ31 | TS031 | Admin Dashboard Top Menu | Verify the features of Top menu | The dashboard should displays top menu with the items like website, booking and docs and are clickable | High
RQ32 | TS032 | Admin Dashboard Left panel Menu | Check the left panel menu of the dashboard | The dashboard should display the left panel witt the main items like dashborad,settings, modules, accounts, CMS. It also has two more main divisions like modules and extras. Modules has divisions like cars, flights, hotels visa and tours. Extras hold options likeoffers, blog, location,coupens, newsletters, payouts and bookings | High
RQ33 | TS033 | Bookings | Verify whether the admin gets redirected to invoice page on clicking on any invoice button provided in the bookings data list | The page redirects to invoice page which displays Payment, Booking Invoice , Booking Details and Guest Information | High
RQ34 | TS034 | Bookings cancellation | Verify whether the data got deleted present in the list of records | Record should be removed from the list upon clicking the RED colored delete button | High
RQ35 | TS035 | Bookings pending to confirmed | Verify whether the count got reflected when booking status was changed from pending to confimed | The count number decreased by 1 in pending Bookings and increased by 1 in confirmed booking | High
RQ36 | TS036 | Website link | Verify whether the Website link present at the top navigation bar of the admin page | Upon clicking the website link it should redirect to it's destination page | High
RQ37 | TS037 | Logout of Admin page | Verify whether the user is able to logout | User should be able to logout from their account on clicking the logout button ang redirects to login page | High