## Defect Report
Project Name: | Php Travels
Document Name: | Defect Report
Created by: | Janza Rasheed A
Date of creation: | 2023-02-10
Date of review:
Defect ID | Application/features/functions/screen | Defect description | EXPECTED RESULT | Actual Result | Business priority [High/Medium/Low] | Reported By | Reported on | Assigned To | Current Status
DFT_01 | Customer Page | Home Tab is missing | Home tab should be visible on the screen | Home tab is missing | Medium | Janza Rasheed | 2023-01-25 | Self | Open
DFT_02 | Agent page | Home Tab is missing | Home tab should be visible on the screen | Home tab is missing | Medium | Janza Rasheed | 2023-01-25 | Self | Open
DFT_03 | Customer | 404 Error Displayed on Clicking Pay Now button | Should able to pay USD50 | Redirecting to page but showing 404 error | High | Janza Rasheed | 2023-01-25 | Self | Open
DFT_04 | Supplier | Revenue Break Down graph displayed blank data | The graph should display the value according to data | Redirecting to page but showing 404 error | Medium | Janza Rasheed | 2023-01-25 | Self | Open
DFT_05 |  | Flight link is missing | Flight link should be presnt at the left side panel and should be clickable | Flight link is missing | High | Janza Rasheed | 2023-01-25 | Self | Open
Supplier
DFT_06 | Supplier | Visa link is missing | Visa link should be presnt at the left side panel and should be clickable | Visa link is missing | High | Janza Rasheed | 2023-01-25 | Self | Open
DFT_07 | Supplier | Supplier valid credentials were not getting accepting in between | User should be able to login with valid credentials any time | wrong credential message was getting diaplayed | High | Janza Rasheed | 2023-02-10 | Self | Open
DFT_08 | Customer | customerr valid credentials were not getting accepting in between | User should be able to login with valid credentials any time | wrong credential message was getting diaplayed | High | Janza Rasheed | 2023-02-10 | Self | Open
DFT_09 | Agent | Agent valid credentials were not getting accepting in between | User should be able to login with valid credentials any time | wrong credential message was getting diaplayed | High | Janza Rasheed | 2023-02-10 | Self | Open
DFT_10 | Customer | Customer URL occasionally won't connect to the Web Server | Should redirect to the Customer Webpage | Shows a Timeout Message | High | Janza Rasheed | 2023-02-10 | Self | Open
DFT_11 | Supplier | Agent URL occasionally won't connect to the Web Server | Should redirect to the Agent Webpage | Shows a Timeout Message | High | Janza Rasheed | 2023-02-10 | Self | Open
DFT_12 | Admin | Admin URL occasionally won't connect to the Web Server | Should redirect to the Admin Webpage | Shows a Timeout Message | High | Janza Rasheed | 2023-02-10 | Self | Open
DFT_13 | Supplier | Supplier URL occasionally won't connect to the Web Server | Should redirect to the Supplier Webpage | Shows a Timeout Message | High | Janza Rasheed | 2023-02-10 | Self | Open
DFT_14 | Supplier | Supplier page doesn’t shows the booking details after clicking bookings tab | The user navigetes to https://phptravels.net/api/admin/bookings and is able to view all the booking details | The user navigetes to https://phptravels.net/api/admin/bookings , but showing error message | Medium | Janza Rasheed | 2023-02-10 | Self | Open